## Bài tập
Project tracking of Capstone
Number | Task name | Note | Person in charge | Status | (%) Test | Start build | Finish build | Deadline
1 | topHeader | đã check responsive , vi trí icon lệch | Phi | Done | 100% | 2023-04-09 | 2023-04-14 | 2023-04-28
2 | Header | đã check responsive , icon lệch | Phi | Done | 100% | 2023-04-09 | 2023-04-15 | 2023-04-28
3 | stdCarousel | Đã check responsive | Phi | Done | 100% | 2023-04-11 | 2023-04-16 | 2023-04-28
4 | stdObjects | Đã check responsive | Phi | Done | 100% | 2023-04-12 | 2023-04-16 | 2023-04-28
5 | stdStudious | Đã check responsive | Phi | Done | 100% | 2023-04-12 | 2023-04-16 | 2023-04-28
6 | stdClasses | Đã check responsive | Long | Done | 100% | 2023-04-11 | 2023-04-11 | 2023-04-28
7 | stdNumbers | Đã check responsive | Long | Done | 100% | 2023-04-12 | 2023-04-12 | 2023-04-28
8 | stdFeedback | Đã check responsive | Long | Done | 100% | 2023-04-14 | 2023-04-14 | 2023-04-28
9 | stdInstructors | Đã check responsive | Long | Done | 100% | 2023-04-14 | 2023-04-14 | 2023-04-28
10 | stdContact | Đã check responsive | Long | Done | 100% | 2023-04-14 | 2023-04-14 | 2023-04-28
11 | Footer | Đã check responsive | Long | Done | 100% | 2023-04-14 | 2023-04-15 | 2023-04-28
12 | Back to top |  | Phi | Done | 100% | 2023-04-14 | 2023-04-14 | 2023-04-28

## Môn học
Môn học
Thêm môn học hoặc khóa học cho học kỳ này
Toán học
Sinh học
Địa lý
Vật lý